## Sheet1
Date | Challenges Faced | Points Discussed | Action Plan
03-06-2025 | 1. Defining scope clearly for AI Operator agent with MCP & browser automation. 2. Complex architecture requiring MCP integration, UI, DevOps, and backend communication. 3. Need for cross-platform compatibility (Electron desktop + hosted web). 4. Deciding initial tech stack and tools. | 1. Decided on Node.js + Electron for desktop, Python backend for automation scripts. 2. UI in React, Electron window management. 3. MCP (Model Control Plane) for structured action execution. 4. Early plan to use Selenium for DOM extraction. 5. Docker setup for microservices where applicable. 6. Assigned tasks based on roles (UI, Backend, MCP, DevOps, Project Management). | 1. Create repo, initial sprint plan, and assign tickets in Jira. 2. Set up Electron scaffold and basic window navigation. 3. Research MCP API and action execution flows.
10-06-2025 | 1. MCP tool creation and API schema definition took more time than expected. 2. Docker setup for multi-service execution was inconsistent across members. 3. Early Selenium tests showed delays in dynamic content loading. | 1. MCP tools creation completed. 2. UI layout prototyping started. 3. Docker file created for Node.js + Python combination. 4. Selenium scripts for automation initiated. | 1. Continue Selenium prototype for DOM extraction. 2. Implement MCP action parser logic. 3. UI to integrate basic chat and display logs.
17-06-2025 | 1. MCP server and tool integration took longer due to API structure changes. 2. UI chat integration faced websocket connection drops. 3. Browser automation scripts not stable for some non-standard sites. | 1. MCP server running with Node.js. 2. Chat UI integration completed. 3. Browser automation testing with Selenium in progress. 4. Docker setup now stable for dev environments. | 1. Connect MCP output to UI. 2. Continue Selenium automation testing. 3. Start preparing slides for interim presentation.
24-06-2025 | 1. Need to polish UI for demo purposes. 2. Browser automation flaky for certain layouts. 3. Tight schedule for interim presentation and MCP testing. | 1. MCP integration demo-ready. 2. UI chat functional. 3. Selenium automation showcased in interim PPT. 4. Discussion on making automation more resilient. | 1. Finalize interim PPT & rehearse. 2. Run full MCP + UI + browser demo.
01-07-2025 | 1. Selenium DOM extraction failing for sites with heavy JS rendering. 2. MCP execution slower than expected due to multiple retries. | 1. Consider switching to alternative DOM extraction methods. 2. Discussed AI model–driven DOM parsing, but models not fully updated with modern frontends. | 1. Research Browser-use library with image processing–based DOM extraction. 2. Start proof of concept.
08-07-2025 | 1. AI model DOM extraction attempts inaccurate for dynamic content. 2. Selenium automation failing for SPAs and shadow DOM elements. | 1. Decided to switch from Selenium + MCP DOM extraction to Browser-use with image processing for reliability. 2. Browser-use bypasses DOM parsing issues by working visually. | 1. Replace Selenium scripts with Browser-use implementation. 2. Adjust MCP to trigger Browser-use actions. 3. Update documentation to reflect architectural change.
15-07-2025 | 1. Adapting existing automation flow to use Browser-use API directly instead of MCP integration. 2. Initial Browser-use setup required fine-tuning image processing thresholds for accurate element detection. | 1. Successful first run of Browser-use API–based automation. 2. DOM extraction now reliable for previously failing pages. 3. Decision to avoid MCP for Browser-use integration to maximize performance and reduce complexity. | 1. Test Browser-use across various websites and scenarios. 2. Prepare final presentation with updated architecture diagram showing Browser-use as the primary automation engine.
22-07-2025 | 1. Reviewing the entire AI Operator workflow to ensure all planned features were implemented. 2. Evaluating project performance, stability, and usability before final submission. 3. Identifying areas for improvement based on team feedback. | 1. Conducted a full evaluation of the AI Operator system, covering UI, automation reliability, and cross-platform performance. 2. Discussed strengths of the final solution and possible enhancements for future versions. 3. Finalized documentation with lessons learned and technical decisions made during the project. 4. Outlined talking points for the final presentation. | 1. Finalize evaluation report and integrate feedback into the closing documentation. 2. Prepare and rehearse final presentation. 3. Conduct one last end-to-end demo to confirm readiness for submission.